# Gantt Chart - Surface Attack Monitoring Tool

Timeline: 12 weeks (W1–W12). Adjust as needed.

Legend: ■ = planned work, blank = no work, [M] = milestone

| Task | Start | End | Dur | Depends | W01 | W02 | W03 | W04 | W05 | W06 | W07 | W08 | W09 | W10 | W11 | W12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Initiation | W1 | W2 | 2 | - | ■ | ■ |  |  |  |  |  |  |  |  |  |  |
| Architecture & Design | W2 | W4 | 3 | Initiation |  | ■ | ■ | ■ |  |  |  |  |  |  |  |  |
| Backend Development | W3 | W8 | 6 | Arch & Design |  |  | ■ | ■ | ■ | ■ | ■ | ■ |  |  |  |  |
| Frontend & UI | W4 | W7 | 4 | Arch, Backend |  |  |  | ■ | ■ | ■ | ■ |  |  |  |  |  |
| Database & Persistence | W3 | W5 | 3 | Arch & Design |  |  | ■ | ■ | ■ |  |  |  |  |  |  |  |
| Security & Compliance | W5 | W9 | 5 | Backend, DB |  |  |  |  | ■ | ■ | ■ | ■ | ■ |  |  |  |
| Testing & QA | W7 | W10 | 4 | Backend, Frontend, Security |  |  |  |  |  |  | ■ | ■ | ■ | ■ |  |  |
| DevOps & Deployment | W8 | W11 | 4 | Backend, Testing |  |  |  |  |  |  |  | ■ | ■ | ■ | ■ |  |
| Documentation & Training | W9 | W12 | 4 | Testing, DevOps |  |  |  |  |  |  |  |  | ■ | ■ | ■ | ■ |
| Project Management | W1 | W12 | 12 | (ongoing) | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ |

Notes:

- Use Courier New in week columns to keep bars aligned.

- Replace W01–W12 with calendar dates as needed.